## Sheet1
JANM
Identified By: MEENU P M Reported To: RUGMA RAGHAV Date: 9 Feb 2023 Environment Details: chrome
Bug ID | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Screenshot | Status
DEF_JANM_01 | Should work all menus under Hamburger | All menus under hamburger is not working | 1.Open Website 2.Click hamburger | Critical |  |  | New
DEF_JANM_02 | Should connect to call while click on phone number | Phone number is disabled | 1.Open Website 2.Click on phone number | Critical |  |  | New
DEF_JANM_03 | Should work View bio button while click on it | View bio option is not working | 1.Open Website 2. Click on view bio | Major |  |  | New
DEF_JANM_04 | Should not overlap each other in different resolutions | Overlaping each other | 1. Open website 2. Check for the allignment | Minor |  |  | New
DEF_JANM_05 | Should give a standard format for mobile number | No format is given | 1. Open website | Major |  |  | New
DEF_JANM_06 | Should not have any grammatical error | Grammatical error is present | 1. Open website 2. Check for grammatical error | Trivial |  |  | New
DEF_JANM_07 | Should have a proper allignment | Allignment is not proper | 1. Open website 2. Check for the allignment | Minor |  |  | New
DEF_JANM_08 | Should work the View all services link while click on it | No details are showing while clicking on it | 1. Open Website 2.click on view all services link | Major |  |  | New
DEF_JANM_09 | Should not have any spelling mistake in the page | Spelling mistake is present | 1. Open Website | Trivial |  |  | New
DEF_JANM_10 | Should work all social media networks while click on it | Not directing to any page | 1. Open Website 2. Click on link given | Major |  |  | New
DEF_JANM_11 | Should give understandable details in location shown in map | Details are not understandable | 1. Open Website 2. Check for the details | Enhancement |  |  | New
DEF_JANM_12 | Should have an understandable format | Page is not user friendly | 1. Open website | Enhancement |  |  | New
DEF_JANM_13 | Should follow a proper font size | Font size is different in contact US details | 1. Open Website 2. Check for font size | Enhancement |  |  | New
DEF_JANM_14 | Should not give same content under different notes given | Same content is written under brain and pain | 1. Open website 2. Check for content | Minor |  |  | New
DEF_JANM_15 | Should be a secured page | No security ensured | 1. Open webpage 2. View on top | Major |  |  | New
DEF_JANM_16 | Should give a correct fax number | Fax number given is incorrect | 1. Open website 2. View on bottom page | Major |  |  | New
DEF_JANM_17 | Should have a clear image displayed | Images are not clear and overlapped | 1. Open website 2. Check for image clarity | Minor |  |  | New
DEF_JANM_18 | Should not repeat same thing again | Our surgeon repeated two times | 1. Open website 2. Check for repetition | Minor |  |  | New
DEF_JANM_19 | Should not contain any breakage while click on any of the options | Complete breakage is occuring while click on menu bar | 1. Open website 2. Click on menu bar 3. Check for social media icons given in the bottom | Major |  |  | New